## Dashboard
Project Dashboard
Project Name: | ShihabVet.com Manual Testing
Delivery Date: | 30-9-2025
Release Number: | v1.0.0
Designed By: | Mohammad Badawi
Environment: | Asus ExpertBook Laptop Windows 11 Pro, RAM 24GB, CPU i5-1235U
Accessibility | Full Access to Database to delete wrong created accounts during testing
Android Versions:
iOS Versions:
Total Number of Test Cases | 64
Number of Passed Test Cases: | 47
Number of Failed Test Cases: | 17

## Test Cases
ShihabVet.com Testing Bug Report
Test Suit Name | Test Suit ID | Test Case Name | Test Case ID | Summary | Preconditions | Test Data | Steps to Reproduce | Expected Result | Actual Result | Status | Prority | Severty | Bug. ID | Recomendations
Sign Up Suit | TS-SU-001 | Valid Sign Up | TC-SU-001 | Sign up with valid credentials (Happy Path) | Go to: shihabvet.com User has no account | Phone Number: Valid First Name: Mohammad Last Name: Badawi Password: ********** Confirm Password: ********** | -Register -Fill in your data -Send OTP -Enter OTP you got -Verify | User should be registered successfully | As expected | Passed | P1 Critical | S1 Blocker
|  | Sign Up with exist user data | TC-SU-002 | Sign Up with existed user mobile number | Go to: shihabvet.com User has account | Same info used in TC1 to first create an account | -Register -Fill in your data (Existed user) -Send OTP -Verify results | Error message of existing user appears | As expected | Passed | P1 Critical | S1 Blocker |  | The error message appears on the top right corner and is not directly visible for users, move it closer
|  | Phone number prefix format validation | TC-SU-003 | Sign up with random phone number starter to check number validation | Go to: shihabvet.com User has account | Phone Number: 1234567890 First Name: Mohammad Last Name: Badawi Password: ********** Confirm Password: ********** | -Register -Fill in your data -Send OTP -Enter OTP you got -Verify | Error message about phone number validation | As expected "Please enter a valid mobile number (Ex: 059XXXXXXXX)." Error appeared | Passed | P1 Critical | S1 Blocker
|  | Phone number prefix format validation (Multible attempts) | TC-SU-004 | Change the phone number prefix | Go to: shihabvet.com User has account | Phone Number: 0(0-9)34567890 First Name: Mohammad Last Name: Badawi Password: ********** Confirm Password: ********** | -Register -Fill in your data -Send OTP -Enter OTP you got -Verify | Error message about phone number validation should appear on all the attepmts (When it meets 05, the third number is 1 not 9) | It accepts numbers starts with 05, no matter what the third number is. | Need Improvements | P2 High | S2 High |  | Fix the phone number validation message.
|  | Invalid Sign Up | TC-SU-005 | Sign up with short phone number | Go to: shihabvet.com User has no account | Phone Number: 05661234 First Name: Mohammad Last Name: Badawi Password: ********** Confirm Password: ********** | -Register -Fill in your data -Send OTP | Error Message should appear on Phone Number field | Error Message: Please enter a valid mobile number (Ex: 059XXXXXXXX). | Passed | P1 Critical | S1 Blocker
|  | Invalid Sign Up | TC-SU-006 | Sign up with long phone number | Go to: shihabvet.com User has no account | Phone Number:05661234567890 First Name: Mohammad Last Name: Badawi Password: ********** Confirm Password: ********** | -Register -Fill in your data -Send OTP | Error Message should appear on Phone Number field | Error Message: Please enter a valid mobile number (Ex: 059XXXXXXXX). | Passed | P1 Critical | S1 Blocker
|  | Invalid Sign Up | TC-SU-007 | Sign up with malformed phone number | Go to: shihabvet.com User has no account | Phone Number:O566I234S6 First Name: Mohammad Last Name: Badawi Password: ********** Confirm Password: ********** | -Register -Fill in your data -Send OTP | Error Message should appear on Phone Number field | Error Message: Please enter a valid mobile number (Ex: 059XXXXXXXX). | Passed | P1 Critical | S1 Blocker
|  | Invalid Sign Up | TC-SU-008 | Sign up with short password | Go to: shihabvet.com User has no account | Phone Number:0566123456 First Name: Mohammad Last Name: Badawi Password: **** Confirm Password: **** | -Register -Fill in your data -Send OTP | Error Message should appear on Password field | Error Message: Minimum length of this field must be equal or greater than 6 symbols. Leading and trailing spaces will be ignored. | Passed | P1 Critical | S1 Blocker
|  | Invalid Sign Up | TC-SU-009 | Sign up with too long password | Go to: shihabvet.com User has no account | Phone Number: First Name: Mohammad Last Name: Badawi Password: (200 character password) Confirm Password: (200 character password) | -Register -Fill in your data -Send OTP -Enter OTP you got -Verify | Error message saying password should not exceed 20-30 character should appear | Accepted the long password | Failed | P1 Critical | S1 Blocker | BUG-001 | Limit the password for at max 30 char
|  | Invalid Sign Up | TC-SU-010 | Sign up with one type characters (small letter only) | Go to: shihabvet.com User has no account | Phone Number: First Name: Mohammad Last Name: Badawi Password: passwordpassword Confirm Password:passwordpassword | -Register -Fill in your data -Send OTP -Enter OTP you got -Verify | Error message saying your password should contain capital, small letter, number and symbols should appear | Accepted the only small letters password | Failed | P1 Critical | S1 Blocker | BUG-002 | Force the password to include diferent character types for improved security
|  | Invalid Sign Up | TC-SU-011 | Sign up with invalid credentials | Go to: shihabvet.com User has no account | Phone Number:0566123 First Name: Mohammad Last Name: Badawi Password: passw Confirm Password: passw | -Register -Fill in your data -Send OTP | Error message should appear on both field asking to enter a valid credentials | As expected | Passed | P1 Critical | S1 Blocker
Log In Suit | TS-LI-002 | Fake Log IN | TC-LI-001 | Log in with valid data, but not registered | Go to: shihabvet.com User has no account | Phone Number: (Valid, not registered) Password: (Valid, not registered) | -Go to Log in page -Fill in your data -Click on Log in | Error message of not existed user should appear, failed to log in | As expected | Passed | P1 Critical | S1 Blocker |  | The error message appears on the top right corner and is not directly visible for users, move it closer
|  | Valid Log IN | TC-LI-002 | Log in with valid credentials (Happy Path) | Go to: shihabvet.com User has account | Phone Number: (Valid) Password: (Valid) | -Go to Log in page -Fill in your data -Click on Log in | User should be successfully logged in | As expected | Passed | P1 Critical | S1 Blocker
|  | Invalid Log IN | TC-LI-003 | Log in with invalid phone number | Go to: shihabvet.com User has account | Phone Number: (Invalid) Password: (Valid) | -Go to Log in page -Fill in your data -Click on Log in | Error Message of wrong data entered should appear | As expected | Passed | P1 Critical | S1 Blocker
|  | Invalid Log IN | TC-LI-004 | Log in with invalid password | Go to: shihabvet.com User has account | Phone Number: (Valid) Password: (Invalid) | -Go to Log in page -Fill in your data -Click on Log in | Error Message of wrong data entered should appear | As expected | Passed | P1 Critical | S1 Blocker
|  | Invalid Log IN | TC-LI-005 | Log in with invalid phone number and password | Go to: shihabvet.com User has account | Phone Number: (Invalid) Password: (Invalid) | -Go to Log in page -Fill in your data -Click on Log in | Error Message of wrong data entered should appear | As expected | Passed | P1 Critical | S1 Blocker
Buy Product Suit | TS-BP-003 | Buy product | TC-BP-001 | Buy product from the home page | Go to: shihabvet.com Logged in or Guest | Portable Luggage Scale | -Scroll down to any product -Click on the product -Add to cart -Checkout -Fill in your address -Click Next -Select paying method -Click Place Order | Order should be placed successfully | As expected | Passed | P2 High | S3 Medium
|  | Buy product | TC-BP-002 | Buy product from inside the product | Go to: shihabvet.com Logged in or Guest | Portable Luggage Scale | -Scroll down to any product -Click the product -Add to cart -Checkout -Fill in your address -Click Next -Select paying method -Click Place Order | Order should be placed successfully | As expected | Passed | P2 High | S3 Medium
|  | Buy product | TC-BP-003 | Buy product by searching it | Go to: shihabvet.com Logged in or Guest | Portable Luggage Scale | -Type product name in search bar -Add to cart -Checkout -Fill in your address (Or choose your saved address) -Click Next -Select paying method -Click Place Order | Order should be placed successfully | As expected | Passed | P2 High | S3 Medium
|  | Buy product | TC-BP-004 | Buy product by navigating it through the categories menu | Go to: shihabvet.com Logged in or Guest | Cattos can chicken | -Click the 3 dashes on the side (Menu) -Cat > Cat Food > Cat Wet Food -Scroll down until you find the desired product -Add to cart -Checkout -Fill in your address (Or choose your saved address) -Click Next -Select paying method -Click Place Order | Order should be placed successfully | As expected | Passed | P2 High | S3 Medium
|  | Buy product | TC-BP-005 | Buy product by navigating it through the categories thumbnails | Go to: shihabvet.com Logged in or Guest | Fish Tank Set 5 pieces | -Click Fish category thumbnail -Scroll Down until you find the product -Add to cart -Checkout -Fill in your address -Next -Select paying method -Place Order | Order should be placed successfully | As expected | Passed | P2 High | S3 Medium
|  | Buy product | TC-BP-006 | Buy 1000000 piece of the same product at once | Go to: shihabvet.com Logged in or Guest | Cattos can chicken | -Search for it -Set quantity 1000000 | Error message should appear telling the maximum quantity to be purchased at once | As expected | Passed | P1 Critical | S2 High
|  | Buy product | TC-BP-007 | Buy 0 piece of a product | Go to: shihabvet.com Logged in or Guest | Cattos can chicken | -Search for it -Set quantity 0 | Error message should appear telling the maximum quantity to be purchased at once | The system correct amount to 1 automaticly (Considered Pass but need improvement) | Need Improvements | P2 High | S3 Medium |  | Show error message to notify the customer about the wrong quantity
|  | Buy product | TC-BP-008 | Buy "asd" piece a product | Go to: shihabvet.com Logged in or Guest | Cattos can chicken | -Search for it -Set quantity "asd" | Error message should appear telling the quantity should be numbers | As expected | Passed | P2 High | S3 Medium
Products Cart Suit | TS-PC-004 | Cart Test | TC-PC-001 | Add product to cart and make sure it has beed added | Go to: shihabvet.com Logged in or Guest | Portable Luggage Scale | -Search for product or find it on the home page -Add to Cart | Product should get added successfully | As expected | Passed | P1 Critical | S1 Blocker
|  | Cart Test | TC-PC-002 | Increase product quantity from inside the cart by clicking the arrows | Go to: shihabvet.com Logged in or Guest | Portable Luggage Scale | -Search for product or find it on the home page -Add to Cart -Open Cart -Increase item quantity -Click Update | Product should get increased successfully | As expected | Passed | P2 High | S2 High
|  | Cart Test | TC-PC-003 | Increase product quantity from inside the cart by typing the new quantity | Go to: shihabvet.com Logged in or Guest | Portable Luggage Scale | -Search for product or find it on the home page -Add to Cart -Open Cart -Increase item quantity -Click Update | Product should get increased successfully | As expected | Passed | P2 High | S2 High
|  | Cart Test | TC-PC-004 | Remove Item from the cart | Go to: shihabvet.com Logged in or Guest | Portable Luggage Scale | -Search for product or find it on the home page -Add to Cart -Open Cart -Click the Delete icon | Product should get removed successfully | As expected | Passed | P2 High | S3 Medium
|  | Cart Test | TC-PC-005 | Apply discount code on the chickout | Go to: shihabvet.com Logged in or Guest | Portable Luggage Scale "Discount Code" | -Search for product or find it on the home page -Add to Cart -Checkout | User should be able to use the discount code option on cart checkout page | There is no discount code option on the cart checkout | Failed | P3 Medium | S3 Medium | BUG-003 | Add discount code option on checkout
|  | Cart Test | TC-PC-006 | Apply discount code from inside the cart | Go to: shihabvet.com Logged in or Guest | Portable Luggage Scale "Discount Code" | -Search for product or find it on the home page -Add to Cart -Hover over My Account -Click My Cart -Type the Discount Code then Apply | User should be able to use the discount code option | As expected | Passed | P3 Medium | S3 Medium
|  | Cart Test | TC-PC-007 | Open Cart page (Usability Test) | Go to: shihabvet.com Logged in or Guest |  | -Click the cart icon | User should be directed to the cart page | Side cart window appeard with no Go to Cart option (Need Improvement) | Need Improvements | P3 Medium | S4 Low |  | Add Go to Cart option in the side cart window
|  | Cart Test | TC-PC-008 | Open Cart page from My Account menu (Usability Test) | Go to: shihabvet.com Logged in or Guest |  | -Hover over My Account -Click on My Cart | User should be directed to the cart page | As expected | Passed | P3 Medium | S4 Low
Shipping Address Suit | TS-SA-005 | Shipping Address | TC-SA-001 | Valid Address (Happy path) | Go to: shihabvet.com Logged in or Guest | First Name: Mohammad Last Name: Badawi Street Address: Rafedia Province: West Bank City: Nablus Phone No: 0566123123 | Checkout a product > Add Address Fill in info Next | Address should be added Successfully | As expected | Passed | P1 Critical | S1 Blocker
|  | Shipping Address | TC-SA-002 | Empty Field Validation | Go to: shihabvet.com Logged in or Guest | null | Checkout a product > Add Address Fill in info Next | Empty fields error message should appear and refuse to save the address | As expected | Passed | P1 Critical | S1 Blocker
|  | Shipping Address | TC-SA-003 | Invalid first and last name | Go to: shihabvet.com Logged in or Guest | 1@3$ | Checkout a product > Add Address Fill in info Next | Invalid name error message should appear | Invalid name accepted | Failed | P2 High | S3 Medium | BUG-004 | Add form data validation
|  | Shipping Address | TC-SA-004 | Very long first and last name | Go to: shihabvet.com Logged in or Guest | !@#$%^&*()qwertyuiop[]asdfghjkl;'zxcvbnm,./ | Checkout a product > Add Address Fill in info Next | Max first, last name of about 40 char error message should appear | Long name accepted, max is 255 char | Failed | P2 High | S3 Medium | BUG-005
|  | Shipping Address | TC-SA-005 | 1 char first and last name | Go to: shihabvet.com Logged in or Guest | % | Checkout a product > Add Address Fill in info Next | Invalid name error message should appear | 1 char name accepted | Failed | P2 High | S3 Medium | BUG-006
|  | Shipping Address | TC-SA-006 | First and last name as numbers | Go to: shihabvet.com Logged in or Guest | 66 | Checkout a product > Add Address Fill in info Next | Invalid name error message should appear | Numbers name accepted | Failed | P2 High | S3 Medium | BUG-007
|  | Shipping Address | TC-SA-007 | Invalid Street Address | Go to: shihabvet.com Logged in or Guest | @@@@@@@@$$$$$$$%!%^^@!^ | Checkout a product > Add Address Fill in info Next | Invalid street address error message should appear | Invalid address accepted | Need Improvements | P2 High | S3 Medium |  | Not consedered as a bug due to mixed data addresses, but can be improved
|  | Shipping Address | TC-SA-008 | Invalid Phone Number | Go to: shihabvet.com Logged in or Guest | asdfgh | Checkout a product > Add Address Fill in info Next | Invalid phone number error message should appear | Invalid phone number accepted | Failed | P2 High | S3 Medium | BUG-008
|  | Shipping Address | TC-SA-009 | Very long phone number | Go to: shihabvet.com Logged in or Guest | asdfghjkl;'][pqoiwiqwebbdmnabdmnabsdmnasbdsadas | Checkout a product > Add Address Fill in info Next | Invalid phone number and max digit count error messages should appear | Invalid long phone number accepted | Failed | P2 High | S3 Medium | BUG-009
|  | Shipping Address | TC-SA-010 | 1 digit phone number | Go to: shihabvet.com Logged in or Guest | w | Checkout a product > Add Address Fill in info Next | Invalid phone number and min digit count error messages should appear | Invalid short phone number accepted | Failed | P2 High | S3 Medium | BUG-010
|  | Shipping Address | TC-SA-011 | Check available Provinces Data and cities | Go to: shihabvet.com Logged in or Guest |  | Checkout a product > Add Address Chech available province Next | West Bank, Jerusalem, 48 Lands should be found as province options | West Bank, Jerusalem, 48 Lands found as province options | Need Improvements | P2 High | S3 Medium |  | Change the City default value to English instead of Arabic (Choose City instead of اختر مدينة)
|  | Shipping Address | TC-SA-012 | Check Company field max char count | Go to: shihabvet.com Logged in or Guest | (500 char) | Checkout a product > Add Address Fill in info Next | Max char count of 100 character error should appear | Max character count of 255 error appeared | Need Improvements | P3 Medium | S4 Low |  | Company name field should be shorter
Account Settings Suit | TS-AS-006 | Account Info | TC-AS-001 | Open Account Settings | Go to: shihabvet.com Must be Logged in |  | Hover over My Account on top right Click on My Account from the list | Should be directed to Account page | As expected | Passed | P2 High | S2 High
|  | Account Info | TC-AS-002 | Visibility of account info | Go to: shihabvet.com Must be Logged in |  | On My Account page | Account info should be visible | Account info visible | Need Improvements | P3 Medium | S4 Low
|  | Account Info | TC-AS-003 | Edit Contact (Account) first and last name | Go to: shihabvet.com Must be Logged in | First Name: Badawi Last Name: Mohammad | On My Account page Under Contact Info Click Edit Change first and last name Click Save | First and last name should be changed successfully | The page refreshes, first and last name stays the same no change | Failed | P2 High | S3 Medium | BUG-011 | Check and validate contact info update fuctionality
|  | Account Info | TC-AS-004 | Edit Contact (Account) email | Go to: shihabvet.com Must be Logged in | example@example.com | On My Account page Under Contact Info Click Edit Check Change Email box Enter the new email Click Save | Email should be changed successfully | The page refreshes, email stays the same no change | Failed | P1 Critical | S2 High | BUG-012 | Check and validate contact info update fuctionality
|  | Account Info | TC-AS-005 | Change Contact (Account) password | Go to: shihabvet.com Must be Logged in | ************* | On My Account page Under Contact Info Click Edit Check Change Password box Clear and enter the current password Enter the new password Click Save | Password should be changed successfully | The page refreshes, password stays the same no change, the second try it worked | Need Improvements | P1 Critical | S2 High |  | Check and validate contact info update fuctionality, make the current password field empty by default
|  | Orders Info | TC-AS-006 | Check orders | Go to: shihabvet.com Must be Logged in |  | On My Account page Click My Orders on the side panel | Orders should be displayed | As expected | Passed | P2 High | S2 High
|  | Orders Info | TC-AS-007 | View order items | Go to: shihabvet.com Must be Logged in |  | On My Account page Click My Orders on the side panel Click the order number | Order items should be displayed | As expected | Passed | P3 Medium | S4 Low
|  | Orders Info | TC-AS-008 | View order invoice | Go to: shihabvet.com Must be Logged in |  | On My Account page Click My Orders on the side panel Click the order number Click Invoices | Order invoice should be displayed | As expected | Passed | P3 Medium | S4 Low
|  | Orders Info | TC-AS-009 | View order shipments | Go to: shihabvet.com Must be Logged in |  | On My Account page Click My Orders on the side panel Click the order number Click Order Shipments | Shipments should be diplayed successfully | As expected | Passed | P3 Medium | S4 Low
|  | Orders Info | TC-AS-010 | Reorder the order | Go to: shihabvet.com Must be Logged in |  | On My Account page Click My Orders on the side panel Click the order number (Or directly Reorder) Click Reorder Choose the item you want to keep or remove Proceed to checkout | User should be able to reorder the same order as previous one with ability of editing the order | As expected | Passed | P2 High | S2 High
|  | Orders Info | TC-AS-011 | Reorder the order then cancel the reorder process | Go to: shihabvet.com Must be Logged in |  | On My Account page Click My Orders on the side panel Click the order number (Or directly Reorder) Click Reorder Choose the item you want to keep or remove Cancel the reorder | User should be able to cancel the reorder | No cancelation button available, and products will be sent automaticly to cart, and user need to remove them one by one manually | Failed | P2 High | S2 High | BUG-013 | Time and effort consuming process and gives a very negative impact on the user experience. In addition, it takes very long time to remove a single product
|  | Orders Info | TC-AS-012 | Print the order | Go to: shihabvet.com Must be Logged in |  | On My Account page Click My Orders on the side panel Click the order number Click Print Order Print the order on paper or PDF | User should get a consestant clear and neat order print | The printed order sheet is unconsestant, neither neat, and the pages are overlapped and some rows will be unreadable | Failed | P3 Medium | S4 Low | BUG-014 | Fix the print layout and margens
|  | Addresses Info | TC-AS-013 | View addresses if existed | Go to: shihabvet.com Must be Logged in |  | On My Account page Click My Addresses on the side panel | User should be able to see his addresses | As expected | Passed | P2 High | S3 Medium
|  | Addresses Info | TC-AS-014 | Add new address | Go to: shihabvet.com Must be Logged in | First Name: Mohammad Last Name: Badawi Street Address: Rafedia Province: West Bank City: Nablus Phone No: 0566123123 | On My Account page Click My Addresses on the side panel Click Add New Address Fill your info Save Address | User should be able to add new address | As expected | Passed | P2 High | S2 High
|  | Addresses Info | TC-AS-015 | Delete address | Go to: shihabvet.com Must be Logged in |  | On My Account page Click My Addresses on the side panel Click Navigate the address to delete Click delete Confirm deletion | User should be able to delete address | As expected | Passed | P3 Medium | S4 Low
|  | Addresses Info | TC-AS-016 | Edit Address | Go to: shihabvet.com Must be Logged in | First Name: Badawi Last Name: Mohammad | On My Account page Click My Addresses on the side panel Click Navigate the address to edit Click edit Update your info Save Address | User should be able to edit address | As expected | Passed | P3 Medium | S4 Low
|  | Addresses Info | TC-AS-017 | Check address required fields | Go to: shihabvet.com Must be Logged in | null | On My Account page Click My Addresses on the side panel Click Add New Address Click Save Address (Without filling info) | User should get error on required fields marked with * symbol | As expected, but Street Address field is reqiured while it has no reqiured * sign | Need Improvements | P3 Medium | S4 Low |  | Add reqiured sign to Street Address
|  | Addresses Info | TC-AS-018 | Check address data max length | Go to: shihabvet.com Must be Logged in | 256 character on each fillable field, then delete chars until it accept it | On My Account page Click My Addresses on the side panel Click Add New Address Fill fields with 256 character Click Save Address | User should get error message on fields telling the maximum field length | Refresh the form and keep fields filled up with no error message, user will not know what is the problem | Failed | P2 High | S3 Medium | BUG-15 | Limit fields max length to logical range and provide error messages telling what is the problem
|  | Addresses Info | TC-AS-019 | Overload fields | Go to: shihabvet.com Must be Logged in | Insert 1000+ character into each field and watch the address form behavior | On My Account page Click My Addresses on the side panel Click Add New Address Overload fields characters (1000+) Watch the form behavior | User should get error message on fields telling the maximum field length | When overloading each field with 1.5 million character and clicking Save Address, it refreshed the page and sent me to login page | Failed | P2 High | S2 High | BUG-16 | It must not accept more than 100 character at max for each field, limit character count per field
Admin Panel Suit | TS-AP-007 | Orders Search Filter | TC-AP-001 | Check Purchase Date filter to search an order | Must have Admin access | Set desired search period | Log in as admin Click Sales on the side panel Click Orders Click Filters Set the purchase date period (From, To) Click Apply Filters | Admin user should get the orders purchased within the selected period | Error message saying: Something went wrong. appeared | Failed | P2 High | S2 High | BUG-17 | Fix the search filters

## Bug Report
ShihabVet.com Testing Bug Report
Bug ID | Title | Summary | Test Data | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity | Notes
BUG-001 | Invalid Sign Up | Sign up with too long password | Phone Number: First Name: Mohammad Last Name: Badawi Password: (200 character password) Confirm Password: (200 character password) | -Register -Fill in your data -Send OTP -Enter OTP you got -Verify | Error message saying password should not exceed 20-30 character should appear | Accepted the long password | P1 Critical | S1 Blocker
Bug ID | Title | Summary | Test Data | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity | Notes
BUG-002 | Invalid Sign Up | Sign up with one type characters (small letter only) | Phone Number: First Name: Mohammad Last Name: Badawi Password: passwordpassword Confirm Password:passwordpassword | -Register -Fill in your data -Send OTP -Enter OTP you got -Verify | Error message saying your password should contain capital, small letter, number and symbols should appear | Accepted the only small letters password | P1 Critical | S1 Blocker
Bug ID | Title | Summary | Test Data | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity | Notes
BUG-003 | No discount option | No field for discount code on the chickout | Portable Luggage Scale "Discount Code" | -Search for product or find it on the home page -Add to Cart -Checkout | User should be able to use the discount code option on cart checkout page | There is no discount code option on the cart checkout | P3 Medium | S3 Medium
Bug ID | Title | Summary | Test Data | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity | Notes
BUG-004 | Invalid address info | Invalid first and last name | 1@3$ | Checkout a product > Add Address Fill in info Next | Invalid name error message should appear | Invalid name accepted | P2 High | S3 Medium
Bug ID | Title | Summary | Test Data | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity | Notes
BUG-005 | Invalid address info | Very long first and last name | !@#$%^&*()qwertyuiop[]asdfghjkl;'zxcvbnm,./ | Checkout a product > Add Address Fill in info Next | Max first, last name of about 40 char error message should appear | Long name accepted, max is 255 char | P2 High | S3 Medium
Bug ID | Title | Summary | Test Data | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity | Notes
BUG-006 | Invalid address info | 1 char first and last name | % | Checkout a product > Add Address Fill in info Next | Invalid name error message should appear | 1 char name accepted | P2 High | S3 Medium
Bug ID | Title | Summary | Test Data | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity | Notes
BUG-007 | Invalid address info | First and last name as numbers | 66 | Checkout a product > Add Address Fill in info Next | Invalid name error message should appear | Numbers name accepted | P2 High | S3 Medium
Bug ID | Title | Summary | Test Data | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity | Notes
BUG-008 | Invalid address info | Invalid Phone Number | asdfgh | Checkout a product > Add Address Fill in info Next | Invalid phone number error message should appear | Invalid phone number accepted | P2 High | S3 Medium
Bug ID | Title | Summary | Test Data | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity | Notes
BUG-009 | Invalid address info | Very long phone number | asdfghjkl;'][pqoiwiqwebbdmnabdmnabsdmnasbdsadas | Checkout a product > Add Address Fill in info Next | Invalid phone number and max digit count error messages should appear | Invalid long phone number accepted | P2 High | S3 Medium
Bug ID | Title | Summary | Test Data | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity | Notes
BUG-010 | Invalid address info | 1 digit phone number | w | Checkout a product > Add Address Fill in info Next | Invalid phone number and min digit count error messages should appear | Invalid short phone number accepted | P2 High | S3 Medium
Bug ID | Title | Summary | Test Data | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity | Notes
BUG-011 | Can't update contact info | can't edit Contact (Account) first and last name | First Name: Badawi Last Name: Mohammad | On My Account page Under Contact Info Click Edit Change first and last name Click Save | First and last name should be changed successfully | The page refreshes, first and last name stays the same no change | P2 High | S3 Medium
Bug ID | Title | Summary | Test Data | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity | Notes
BUG-012 | Can't update contact email | Can't update contact's email | New Valid Email | On My Account page Under Contact Info Click Edit Check Change Email box Update the email Click Save | Email should be changed successfully | The page refreshes, email stays the same no change | P2 High | S2 High
Bug ID | Title | Summary | Test Data | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity | Notes
BUG-013 | Reorder malfunction | Products go to cart when reordering an order then cancel the reorder process |  | On My Account page Click My Orders on the side panel Click the order number (Or directly Reorder) Click Reorder Choose the item you want to keep or remove Cancel the reorder | User should be able to cancel the reorder | No cancelation button available, and products will be sent automaticly to cart, and user need to remove them one by one manually | P2 High | S2 High
Bug ID | Title | Summary | Test Data | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity | Notes
BUG-014 | Print page unconsestant | Printed page is unconsestant and broken |  | On My Account page Click My Orders on the side panel Click the order number Click Print Order Print the order on paper or PDF | User should get a consestant clear and neat order print | The printed order sheet is unconsestant, neither neat, and the pages are overlapped and some rows will be unreadable | P3 Medium | S4 Low
Bug ID | Title | Summary | Test Data | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity | Notes
BUG-015 | Very long inpit field capacity | Fields can save up to 255 character info including name, address, company, and phone number | 256 character on each fillable field, then delete chars until it accept it | On My Account page Click My Addresses on the side panel Click Add New Address Fill fields with 256 character Click Save Address | User should get error message on fields telling the maximum field length | Refresh the form and keep fields filled up with no error message, user will not know what is the problem | P2 High | S3 Medium
Bug ID | Title | Summary | Test Data | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity | Notes
BUG-016 | Field overloadable | Fields can be overloaded with more than 1 million character | Insert 1000+ character into each field and watch the address form behavior | On My Account page Click My Addresses on the side panel Click Add New Address Overload fields characters (1000+) Watch the form behavior | User should get error message on fields telling the maximum field length | When overloading each field with 1.5 million character and clicking Save Address, it refreshed the page and sent me to login page | P2 High | S2 High
Bug ID | Title | Summary | Test Data | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity | Notes
BUG-017 | Orders search filter malfunctioning | Can't use purchase date filter for search | Set desired search period | Log in as admin Click Sales on the side panel Click Orders Click Filters Set the purchase date period (From, To) Click Apply Filters | Admin user should get the orders purchased within the selected period | Error message saying: Something went wrong. appeared | P2 High | S2 High

## RTM
ShihabVet Requirement Traceability Matrix (RTM)
Requirement ID | Requirement Name | Requirement Description | Type of Requirement | Test Suite ID | Priority Level | Potential Risk | Requirement Status | Acceptance Criteria | Test Cases | Objectives and Goals | Assigned To
REQ-001 | User Sign Up | Make sure users signs up with valid data | Functional | TS-SU-001 | P1 Critical | Users signup with invalid data and their accounts can't be restored | Completed | User can sign up with valid and logical data length to maintain usability and security | TC-SU-001 TC-SU-002 TC-SU-003 TC-SU-004 TC-SU-005 TC-SU-006 TC-SU-007 TC-SU-008 TC-SU-009 TC-SU-010 TC-SU-011 | Improve the website security and consistancy | Mohammad Badawi
REQ-002 | User Log In | Make sure users log in with valid data | Functional | TS-LI-002 | P1 Critical | Logging in with invalid data may lead to block the users upon security reasons | Completed | User can log in with valid and logical data length to maintain usability and security | TC-LI-001 TC-LI-002 TC-LI-003 TC-LI-004 TC-LI-005 | Improve the website security and consistancy | Mohammad Badawi
REQ-003 | Validate Buying Product Easiness | Make sure buying product is easy with no errors or blockers | Functional + Non-Functional | TS-BP-003 | P2 High | Boring, long and complicated buying process may lead to high customer bouncing rate and users dropping the website | Completed | Easy and direct purchasing workflow | TC-BP-001 TC-BP-002 TC-BP-003 TC-BP-004 TC-BP-005 TC-BP-006 TC-BP-007 TC-BP-008 | Improve the website usability | Mohammad Badawi
REQ-004 | Validate Well Cart Functionality and behavior | Validate cart functionality and behavior | Functional + Non-Functional | TS-PC-004 | P2 High | Complicated and malfunctioning cart may lead to the customer dropping the order | Completed | User being able to add, remove, edit, open and close cart easily without complications | TC-PC-001 TC-PC-002 TC-PC-003 TC-PC-004 TC-PC-005 TC-PC-006 TC-PC-007 TC-PC-008 | Improve the website usability | Mohammad Badawi
REQ-005 | Validate Shipping Address Functionality and behavior | Validate address data validation and form functionalityt | Functional | TS-SA-005 | P2 High | Wrong addresses may lead to random orders without real addresses, and if the address is missing info the delivery will drop the order | Completed | User should be forced to use a valid address info by using dropdown lists when ablicable and doable | TC-SA-001 TC-SA-002 TC-SA-003 TC-SA-004 TC-SA-005 TC-SA-006 TC-SA-007 TC-SA-008 TC-SA-009 TC-SA-010 TC-SA-011 TC-SA-012 | Improve the website control and monitoring | Mohammad Badawi
REQ-006 | Validate Account Setting Functionality | Make sure the account settings are working properly | Functional | TS-AS-006 | P2 High | If the users wan not able to edit his/her info they will feel the low quality and will lead to negative impact about the company | Completed | User should be able to edit or update his/her info easily while maintaining security and privacy | TC-AS-001 TC-AS-002 TC-AS-003 TC-AS-004 TC-AS-005 TC-AS-006 TC-AS-007 TC-AS-008 TC-AS-009 TC-AS-010 TC-AS-011 TC-AS-012 TC-AS-013 TC-AS-014 TC-AS-015 TC-AS-016 TC-AS-017 TC-AS-018 TC-AS-019 | Improve the user control and maintainability of the account, which will lead to uprising trustworthness | Mohammad Badawi
REQ-007 | Validate Orders Search Filter Functionality | Make sure orders searching filter is working properly | Functional | TS-AP-007 | P3 Medium | Malfunctioning search filters will make picking up a specific orders period very hard and time consuming, its very critical for reporting | Completed | Admin should be able to apply all the search filters to make it easy for him/her to prepare reports etc... | TC-AP-001 | Improve the admin control and usability of the dashboard and the ability of making reports | Mohammad Badawi

## Test Summary Report
ShihabVet Test Summary Report
Test Cycle | System Test
Executed | Passed | 47
| Failed | 17
| Total Tests Executed (Passed + Failed) |  |  |  |  | 64
Pending | [5 empty] | 0
In Progress | [5 empty] | 0
Blocked | [5 empty] | 0
(Sub-Total) Test Planed | [5 empty] | 64
[Pending - In Progress - Blocked - Test Executed]
Functions (Test Scenarios) | Description | TCs Excuted % | TCs Passed % | TCs pending | Priority | Remarks
Sign Up | Make sure users signs up with valid data | 100% | 82% | 0% | High
Log In | Make sure users log in with valid data | 100% | 100% | 0% | High
Buy Product | Make sure buying product is easy with no errors or blockers | 100% | 100% | 0% | High
Product Cart | Validate cart functionality and behavior | 100% | 87.5% | 0% | High
Shipping Address | Validate address data validation and form functionalityt | 100% | 42% | 0% | High
Account Settings | Make sure the account settings are working properly | 100% | 68% | 0% | High
Admin Panel | Make sure orders searching filter is working properly | 100% | 0%% | 0% | High